## Sheet1
IT Dashboard Summer Roadmap |  |  | Important Note: This document is illustrative and subject to change. The sequencing and time allocations will naturally adjust as the team progresses through FY 2021 development.
Item | Sprint 10 | Sprint 11 | Sprint 12 | Sprint 13 | Sprint 14
Sprint Planning | 2019-05-24 | 2019-06-14 | 2019-07-10 | 2019-07-26 | 2019-08-16
Sprint Review | 2019-06-13 | 2019-07-09 | 2019-07-25 | 2019-08-15 | 2019-09-05
MAX Lane | N/A | N/A | PHP 7 Regression | PHP 7 Launch | Production Go-live
FY 2021 Swim Lane | FY 2021 Environment Creation | Deployment Report | Risks Report | Business Case / SIR Updates | SIL Updates
| Contracts Refactor |  |  | IT Budget Updates | UAT Findings
UAT Findings
Production Bugs | Critical Only | Critical Only | Critical Only | Critical Only | Critical Only
Documents |  | 95% Data Dictionary | 95% Validations List | 95% Final Submission Instructions
Note: Data Feeds and XSDs are updated along with functional enhancements
ILLUSTRATIVE